## Sheet1
ID | Short description | Long Description | Complexity | Duration | Assigned to | Start by | End by | Classification
1 | wholesale renaming | Wholesale renaming of files, with associated name changes in the src (variable names and file names have been changed to be in lowercase, without ellipses, etc.). This was done using a combination of sed, and just going through each file and all the data objects Victoria was using. | Medium | 2 days | David |  | done | refactoring
2 | parsing old code | Parsing Old Code, and understanding purpose of each file and functions within | High |  | David | ongoing |  | programming
3 | coded macroeconomic data munging file based off of old work | Finished a macroecnomic data munging file, which was sorely needed. In the old code, the macroeconomic variables needed for the PPNR and NCO autoregression were being computed (incorrectly, with misalignments or unnecessary NA’s in the resulting data frame), and then appended to a much larger file of macroeconomic variables which were NOT needed for the regression. | High | 6 days | David | 2015-02-12 | 2015-02-18 | implementing model
4 | refactored somecode manually, then discovered formatR | Researched and then ran formatR to clean up code further (for example, to change = to <- wherever needed, fix indentation, etc.). Lost time doing these changes manually, before discovering the formatR package | medium | 1 day | David |  | done | refactoring
5 | read ClASS Model whitepapers | Spent time reading the CLASS Model whitepapers, and trying to figure out what I should be programming, and the general scope of the project | medium | 1 day total | David |  | ongoing | implementing model
6 | learning R programming language | Spent considerable time just learning the R programming language, which I was not familiar with at all prior to the start of this project. | high | 10 days | David |  | ongoing | programming
7 | edit the forecasting main code, to run the forecasts for future NCO and PPNR after calibration |  | high | 5 days | David |  |  | model development
8 | munge the balance ratio data |  | high | 3 days | David |  | ongoing | programming
9 | recode find ppnr 200 largest banks by asset. Isolate the remaining |  | medium | 3 days | David |  | ongoing | programming
10 | do same for NCO |  | medium | 3 days | David |  |  | programming
11 | edit the existing calibration functions for the NCO and PPNR |  | high | 5 days | David |  |  | model development
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21